## SETTINGS
EARNED VALUE MANAGEMENT |  |  | SUPPORT
|  |  | v1 | ET0330012007001
|  |  | Product Page | Earned Value Management Template
|  |  | Site | www.indzara.com
|  |  | E-mail | indzara@gmail.com
|  |  | Password | indzara
PROJECT START DATE | 2021-01-01 | STEPS
PROJECT END DATE | 2021-01-31 | 1. Enter basic project information in SETTINGS
AGGREGATE | WEEKLY | 2. Enter Plan information in PLAN sheet
PLANNING UNIT | COST | 3. Enter Actual work performed in ACTUAL sheet
COST ENTRY | ACTUAL COST | 4. Enter Actual Cost in ACTUAL_COST sheet
CURRENCY | OTHER | 5. View EVM sheet for the output calculations

## PLAN
PERIOD |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
ENTER PLANNED COST | WEEK END DATE --> | 1: 2021-01-07; 2: 2021-01-14; 3: 2021-01-21; 4: 2021-01-28
TASK | COST PER HOUR | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | P13 | P14 | P15 | P16 | P17 | P18 | P19 | P20 | P21 | P22 | P23 | P24 | P25 | P26 | P27 | P28 | P29 | P30 | P31 | P32 | P33 | P34 | P35 | P36 | P37 | P38 | P39 | P40 | P41 | P42 | P43 | P44 | P45 | P46 | P47 | P48 | P49 | P50 | P51 | P52 | TOTAL
Task One | 10 | 2: 50; 3: 50; 4: 50 | 150
Task Two | 20 | 1: 10; 2: 25; 3: 25; 4: 25 | 85
Task Three | 25 | 1: 5; 2: 10; 3: 50; 4: 10 | 75

## ACTUAL
PERIOD |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
ENTER ACTUAL % OF WORK DONE | WEEK END DATE --> | 1: 2021-01-07; 2: 2021-01-14; 3: 2021-01-21; 4: 2021-01-28
TASK | TOTAL % | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | P13 | P14 | P15 | P16 | P17 | P18 | P19 | P20 | P21 | P22 | P23 | P24 | P25 | P26 | P27 | P28 | P29 | P30 | P31 | P32 | P33 | P34 | P35 | P36 | P37 | P38 | P39 | P40 | P41 | P42 | P43 | P44 | P45 | P46 | P47 | P48 | P49 | P50 | P51 | P52
Task One | 70% | 1: 15%; 2: 5%; 3: 10%; 4: 10%; 5: 10%; 6: 20%
Task Two | 75% | 1: 20%; 2: 5%; 3: 5%; 4: 20%; 5: 5%; 6: 20%
Task Three | 90% | 1: 10%; 2: 10%; 3: 10%; 4: 50%; 5: 5%; 6: 5%

## ACTUAL_COST
PERIOD |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
ENTER ACTUAL COST | WEEK END DATE --> | 1: 2021-01-07; 2: 2021-01-14; 3: 2021-01-21; 4: 2021-01-28
TASK | TOTAL | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | P13 | P14 | P15 | P16 | P17 | P18 | P19 | P20 | P21 | P22 | P23 | P24 | P25 | P26 | P27 | P28 | P29 | P30 | P31 | P32 | P33 | P34 | P35 | P36 | P37 | P38 | P39 | P40 | P41 | P42 | P43 | P44 | P45 | P46 | P47 | P48 | P49 | P50 | P51 | P52
Task One | 250 | 1: 100; 2: 200; 3: -50
Task Two | 400 | 1: 100; 2: 50; 3: 200; 4: 50
Task Three | 925 | 1: 500; 2: 200; 3: 25; 4: 200

## H_CALC (hidden)
Number of columns of valid dates - used in snapshot dates data validation
4
| 2020-12-31 | 2021-01-07 | 2021-01-14 | 2021-01-21 | 2021-01-28 | 2021-02-04 | [47 empty] | TOTAL
| PLANNED | 15 | 85 | 125 | 85 | 0 | [47 empty] | 310
| EARNED | [52 empty] | 0
| ACTUAL COST | [52 empty] | 0
CUMULATIVE | PLANNED VALUE | 15 | 100 | 225 | 310 | 310 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| EARNED VALUE | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| ACTUAL COST | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
DATE
CPI
SPI
| AS OF SNAPSHOT DATE | 2016-06-30
SNAPSHOT PERIOD
PLANNED VALUE
EARNED VALUE
ACTUAL COST
SCHEDULE VARIANCE
COST VARIANCE

## EVM
SNAPSHOT DATE | 2016-06-30
|  | VARIANCES |  | FORECASTING
PROJECT START DATE | 2021-01-01 | SCHEDULE VARIANCE (SV) | AHEAD OF SCHEDULE | METHOD | CPI
PROJECT END DATE | 2021-01-31 | COST VARIANCE (CV) | UNDER PLANNED COST | ESTIMATE TO COMPLETE (ETC)
PLANNED VALUE (PV) |  |  |  | ESTIMATE AT COMPLETION (EAC)
EARNED VALUE (EV) |  | INDICES |  | VARIANCE AT COMPLETION (VAC)
ACTUAL COST (AC) |  | SCHEDULE PERFORMANCE INDEX (SPI)
BUDGET AT COMPLETION (BAC) | 310 | COST PERFORMANCE INDEX (CPI) |  | ESTIMATED COMPLETION DATE | #VALUE!
TO-COMPLETE PERFORMANCE INDEX (TCPI)
|  | Option 1: To Complete On Planned Budget | HARDER TO COMPLETE
|  | Option 2: To Complete on new EAC Budget | HARDER TO COMPLETE
Note on E5: indzara: SV = EV - PV
Note on E6: indzara: CV = EV - AC
Note on E9: indzara: SPI = EV / PV
Note on E10: indzara: CPI = EV / AC
Note on E12: indzara: TCPI = (BAC - EV) / (BAC - AC)
Note on E13: indzara: TCPI = (BAC - EV) / (EAC - AC)

## TERMS
TERM | ABBREVIATION | DEFINITION | NOTES
PLANNED VALUE | PV | Authorized Budget assigned to the scheduled work | Also called as Budgeted Cost for Work Scheduled (BCWS)
EARNED VALUE | EV | Measure of actual work performed expressed as budget authorized for that work | Also called as Budgeted Cost for Work Performed (BCWP)
ACTUAL COST | AC | Actual cost incurred for the work performed | Also called as Actual Cost of Work Performed (ACWP)
SCHEDULE VARIANCE | SV | Amount by which project is ahead or behind plan | = EV - PV
COST VARIANCE | CV | Amount by which actual cost is ahead or behind planned cost | = EV - AC
BUDGET AT COMPLETION | BAC | Total Budget assigned to the entire plan
SCHEDULE PERFORMANCE INDEX | SPI | Measure of Schedule efficiency expressed as Earned Value to Planned Value | = EV/PV
COST PERFORMANCE INDEX | CPI | Measure of Cost efficiency expressed as Earned Value to Actual Cost | = EV/AC
ESTIMATE AT COMPLETION | EAC | Expected Total Cost of project = sum of Actual Cost till date and Estimate To Complete remaining work Option 1) Remaining Work will be done at the planned/budgeted rate Option 2) Remaining Work will be done at the present CPI Option 3) Remaining Work will be done considering present SPI and CPI | Option 1) = AC + (BAC - EV) Option 2) = BAC/CPI Option 3) = AC + [(BAC- EV)/(CPI * SPI)]
ESTIMATE TO COMPLETE | ETC | Expected Cost to finish the remaining project work | = EAC - AC
VARIANCE AT COMPLETION | VAC | Estimated difference in cost at the completion of the project compared to Plan | = BAC - EAC
TO-COMPLETE PERFORMANCE INDEX | TCPI | Measure of the cost performance required with the remaining resources to meet goal. Work Remaining/Funds Remaining Option 1) Efficiency that must be maintained to complete on Planned Budget Option 2) Efficiency that must be maintained to complete on current EAC | Option 1) = (BAC- EV)/(BAC- AC) Option 2) = (BAC- EV)/(EAC- AC)
ESTIMATED COMPLETION DATE | ECD | Expected Completion Date of the project | = Project Start Date + (Planned Duration/SPI)